## Foglio1
Item | Reference Specification | Reference Pharagraph | Name (test /requirement/ standard) | Requirement Description | Variant ??? Limit / Indication
1 | TDR | §CDS | CDS (Component Development Sheet) | CDS not provided in RFQ package. Required for: timing plan, ED&D cost precision, and part configuration definition. | ❌ BLOCKED – Request from customer PM
2 | TDR | §Timing | Vehicle Development Plan (VP/PS/SOP dates) | Vehicle development calendar not provided. Required to complete Supplier Timing (Deliverable #5) and APQP milestones. | ❌ BLOCKED – Request from customer PM
3 | TDR / CTS | §3D / §Design | Initial 3D CAD Data | No 3D layout data provided. Required to confirm routing, connector count, clip positions, and accurate costing. | ❌ BLOCKED – Request from customer TE (.prt / Parasolid)
4 | TDR | #1 | Native UG / TcAE Capability | Stellantis requires native Unigraphics (.prt) and TcAE access. Different 3D formats not accepted. | 🔵 PENDING – Internal capability to be confirmed
5 | CTS | §Technical Spec / Materials | Internal Nickel Plating of Metallic Pipe (9.02145/02) | CTS states: 'Metallic pipe is required internal nickel plate treatment.' Plating capability or pre-plated tube sourcing TBD. | 🔵 PENDING – In-house plating or qualified sub-supplier TBD
6 | PF.90197 | §9.5 | Pulsating Pressure Test (300,000 / 600,000 cycles) | Long-duration durability test. In-house test capability not confirmed. 45 samples required per R95C90. | 🔵 PENDING – Likely outsourced to 3rd party lab (TÜV/SGS)
7 | PF.90197 | §9.4 | Vibration Cycle Test (60h, 3-axis PSD, R95C90) | Tri-axial vibration durability. In-house capability TBD. 45 samples × 60h. | 🔵 PENDING – Likely outsourced
8 | PF.90197 | §8.2 | MiniSHED Evaporative Emission Test (EMEA) | Market applicability (EMEA?) not confirmed. If applicable, 15 samples, specialized test chamber required. | 🔵 PENDING – Confirm KP1 target market first
9 | PF.90197 | §5.4 | CaCl2 Corrosion Resistance (EMEA only) | EMEA market only. Test applicability depends on confirmed KP1 target market. | 🔵 PENDING – Confirm market scope
10 | PF.90197 / PF.90068 | §6.2.1 / PF.90068 | DEF Line (PF.90068) Manufacturing Experience | KP1 includes DEF Line Assy – Middle. PF.90068 is a separate 37-page standard. First-time experience with DEF lines to be confirmed. | 🔵 PENDING – Internal experience assessment required
11 | SD-M0008/03 | §Pre-approval | Plastic Tube Material Pre-approval Status | Fuel line plastic materials must be pre-approved per SD-M0008/03 list. Supplier's proposed materials approval status unknown. | 🔵 PENDING – Confirm material supplier approval status
12 | PF.90298 | §Pre-approval | Quick Connector Supplier Pre-approval | Quick connectors (metal, dual-latch) must be from Stellantis-approved supplier list. Connector Tier 2 supplier TBD. | 🔵 PENDING – Confirm QC supplier Stellantis approval status
13 | KP1 Damper PPTX | §Assembly | Damper Assembly – Specified Supplier | KP1 damper has specific engineering drawing. Typically supplied by a designated Tier 2 supplier. Cooperation and supply chain TBD. | 🔵 PENDING – Confirm damper supplier availability
14 | PF.90197 | §7.2 | 100% Online Leak Test Capability (≤15μm VLD) | Production line must demonstrate detection of 15μm × 3mm VLD for liquid fuel lines. Dedicated equipment required. | 🔵 PENDING – Production line equipment investment assessment
15
16
17
18
19
20